National University of Lesotho

Department of Mathematics and Computer Science

NUL Attendance Management System

CS3430: System Analysis and Logical Design

Post-Project Review

Structured Evaluation of Project Outcomes, Process & Team

Document Type: Post-Project Review

Project: NUL Attendance Management System

Project Period: 16 February 2026 – 8 May 2026

Review Date: 8 May 2026

Prepared by: All Team Members — CS3430

# 1. Purpose

This Post-Project Review provides a structured evaluation of the NUL Attendance Management System project against its original objectives, constraints, and quality standards. It differs from the Lessons Learned Report in that it focuses on outcomes and measurements rather than reflective insights — assessing whether the project succeeded, by how much, and against what criteria.

# 2. Objectives Review

| Original Objective | Target | Outcome | Met? |
| --- | --- | --- | --- |
| Develop a secure login system for administrators and lecturers | Functional JWT auth on all protected routes | Implemented for admin and lecturer roles | Yes |
| Implement CRUD operations for attendance records | Full create, read, update, delete by lecturers and admins | All four operations functional | Yes |
| Generate automated attendance summary reports | Reports filterable by student, course, or date range | Report generation implemented | Yes |
| Improve record accuracy vs paper-based system | At least 90% accuracy improvement | Digital records eliminate transcription errors entirely | Yes |
| Deliver a tested, deployable system by 10 April 2026 | System complete and submitted by deadline | System delivered on deadline | Yes |

# 3. Scope Review

## 3.1 In-Scope Items — Delivery Status

| In-Scope Item | Delivered | Quality Assessment |
| --- | --- | --- |
| User authentication (login/logout) | Yes | Functional — JWT implemented |
| Role-based access control | Yes | Admin, Lecturer, Student roles enforced |
| Student registration & profile management | Yes | Admin CRUD complete |
| Course creation & management | Yes | Admin functionality complete |
| Attendance CRUD by lecturers | Yes | All operations working |
| Automated attendance report generation | Yes | Reports by student/course/date range |
| View attendance records | Yes | Available per role permissions |

## 3.2 Out-of-Scope Items — Boundary Held

| Out-of-Scope Item | Was it introduced? | Notes |
| --- | --- | --- |
| Mobile application | No | Boundary respected throughout |
| NUL system integration | No | No attempt made to connect to existing NUL infrastructure |
| Financial / fee modules | No | Not requested, not built |
| Production cloud hosting | No | Academic local deployment only |

# 4. Schedule Review

| Phase | Planned Dates | Actual Dates | Variance | Assessment |
| --- | --- | --- | --- | --- |
| Initiation & Planning | W1–W2 (16–27 Feb) | W1–W2 | On time | Met |
| Risk Plan | W2–W3 (23 Feb – 6 Mar) | W2–W3 | On time | Met |
| Analysis & System Models | W3–W5 (2–20 Mar) | W3–W5 | On time | Met |
| Design & UI Prototype | W4–W6 (9–27 Mar) | W4–W7 (partial) | +4 days | Slightly late |
| Implementation | W5–W8 (16 Mar – 10 Apr) | W5–W9 (core complete W8) | +4–7 days on sub-tasks | Late but recovered |
| Testing & UAT | W8–W10 (6–24 Apr) | W9–W10 | Shifted by ~1 week | Completed |
| Closure & Handover | W11–W12 (27 Apr – 8 May) | W11–W12 | On time | Met |

# 5. Quality Review

| Quality Area | Standard Set | Outcome | Rating |
| --- | --- | --- | --- |
| Code review compliance | 100% PRs reviewed before merge | 100% maintained throughout | Excellent |
| TypeScript compile errors at submission | 0 errors | 0 errors at final submission | Excellent |
| Functional requirements delivered | 100% of in-scope features | 100% delivered | Excellent |
| Test coverage (CRUD flows) | All flows tested | All major flows tested in UAT | Good |
| Documentation completeness | All 21 deliverables produced | All 21 deliverables complete | Excellent |
| Integration stability | Frontend, backend, DB fully integrated | Fully integrated and stable at submission | Good |
| Schedule adherence | All milestones on time | Implementation sub-tasks 4–7 days late | Satisfactory |

# 6. Team Performance Review

| Member | Student No. | Key Contribution | Overall Performance |
| --- | --- | --- | --- |
| Makhang, L.M. | 202322596 | Project leadership, Initiation and Closure documentation, scope management | Good |
| Tsita, S.T. | 202322646 | Analysis phase, system models, business rules, Planning documentation | Good |
| Manyeli, H.M. | 202002241 | UI prototype (Figma), React/TSX frontend, design phase delivery | Good |
| Rakoloi, B.R. | 202321274 | Node.js backend, MySQL integration, API implementation | Satisfactory |

All team members contributed meaningfully to the project. The 'Satisfactory' rating for 202321274 reflects time management challenges during the implementation sprint, not a shortfall in technical contribution or commitment.

# 7. Stakeholder Satisfaction Assessment

| Stakeholder | Expectation | Outcome | Satisfaction |
| --- | --- | --- | --- |
| CS3430 Lecturer (Client) | Full PM and SDLC documentation + working system | All 21 documents produced; system delivered | Expected: High |
| Project Team | Functional system, academic credit, real-world experience | System works; extensive documentation; significant learning | High |
| Simulated NUL Users | Web-based system replacing paper registers | Web app with full CRUD, reports, and role-based access | Expected: High |

# 8. Key Risks — Retrospective Assessment

| Risk | Likelihood (Planned) | Did It Occur? | Impact | How Managed |
| --- | --- | --- | --- | --- |
| Team member unavailability | Medium | Partially — competing workloads | Low — managed through task redistribution | Effective |
| Scope creep | Medium | No | N/A | Scope boundary held firm throughout |
| Technology issues | Low | Yes — TKinter incompatibility | Medium — required CR-001 and re-learning | Effective via formal change request |
| Schedule overrun | Low | Yes — implementation sub-tasks | Low — absorbed within overall window | Managed — no deadline impact |

# 9. Overall Project Verdict

The NUL Attendance Management System project is assessed as successfully completed. All primary objectives were met, all in-scope deliverables were produced, and the final system was delivered on deadline. The project encountered real challenges — a technology change, integration complexity, and schedule pressure — that were managed professionally and transparently throughout.

The project produced not only a functional web-based attendance system but also a comprehensive set of 21 project management and SDLC documents, a formal change request, and a team that emerged with significantly improved skills in TypeScript, React, Node.js, MySQL integration, and project governance.

This is considered a strong outcome for a 12-week academic software project.

# 10. Sign-Off

| Role | Name / Student No. | Signature | Date |
| --- | --- | --- | --- |
| Project Lead | Makhang, L.M. — 202322596 |  | May 2026 |
| Team Member | Tsita, S.T. — 202322646 |  | May 2026 |
| Team Member | Manyeli, H.M. — 202002241 |  | May 2026 |
| Team Member | Rakoloi, B.R. — 202321274 |  | May 2026 |

Prepared by the CS3430 Project Team — National University of Lesotho