National University of Lesotho

Department of Mathematics and Computer Science

HEADCOUNT — NUL Attendance Management System

CS3430: System Analysis and Logical Design

Post-Project Review

Structured Evaluation of HEADCOUNT — Outcomes, Process & Quality

Document Type: Post-Project Review

System: HEADCOUNT — headcount-nine.vercel.app

Project Period: 16 February 2026 – 10 April 2026

Review Date: 10 April 2026

Prepared by: All Team Members — CS3430

# 1. Purpose

This Post-Project Review provides a structured, measurement-focused evaluation of the HEADCOUNT project against its original objectives, constraints, change requests, and quality standards. A key context for this review is that the project deadline was moved forward to 10 April 2026 by the course lecturer — an external change outside the team’s control. This occurred while the team was mid-implementation, leaving a significantly shorter window than originally planned to complete all remaining features, integration, deployment, and documentation. The team’s performance across every dimension of this review must be read in that context.

# 2. Original Objectives — Delivery Assessment

| Original Objective | Target | Outcome | Met? |
| --- | --- | --- | --- |
| Develop a secure login system for administrators and lecturers | JWT auth on all protected routes; bcrypt password hashing | Implemented for all three roles; admin requires additional secret code gate | Yes |
| Implement CRUD operations for attendance records | Full create, read, update, delete by lecturers | All four operations functional; manual override available; present/late/absent ENUM enforced | Yes |
| Generate automated attendance summary reports | Reports filterable by student, course, or date range | Report generation implemented; previewable in UI; downloadable as formatted PDF/ CSV | Yes |
| Improve record accuracy over paper-based system | At least 90% accuracy improvement | Digital records eliminate transcription errors; code-based capture with timer enforces accuracy at source | Yes |
| Deliver a tested, deployable system by 10 April 2026 | System complete and publicly accessible | System live at headcount-nine.vercel.app; Railway + Vercel deployment stable | Yes |

# 3. Scope Review

## 3.1 Original Scope — Delivery Status

| In-Scope Item | Delivered | Notes |
| --- | --- | --- |
| User authentication (login/logout) | Yes | JWT; admin additionally gated by secret code |
| Role-based access control | Yes | Admin, Lecturer, Student — API middleware enforced |
| Student registration & profile management | Yes | Admin CRUD; programme linked to all associated depts. |
| Course creation & management | Yes | Multi-departmental; listed per dept. per year of study |
| Attendance CRUD by lecturers | Yes | Code-based + manual; present/late/absent |
| Automated attendance report generation | Yes | Preview + PDF; semester and yearly scope |
| View attendance records | Yes | Per role — student sees own, lecturer sees their courses, admin sees all |

## 3.2 CR-002 Scope Additions — Delivery Status

| CR-002 Feature | Status | Notes |
| --- | --- | --- |
| Attendance code system (15-min timer, present/late) | Complete | AttendanceSession model; code generation; timer; phase logic |
| Session duration choice (50-min / 1hr 50-min) | Complete | classDuration field on AttendanceSession |
| Session persistence (no termination on nav away) | Complete | Session persists until lecturer explicitly ends it |
| Class initiation from My Classes only | Complete | Dashboard shows status only; no nav to take-attendance |
| Manual attendance marking by lecturer | Complete | Lecturer can mark present for students who cannot submit code |
| Role-specific colour theming | Complete | Admin: red/orange · Lecturer: forest/ocean · Student: default/royal |
| Dark/light mode (system theme matching) | Substantially complete | prefers-color-scheme implemented; white patches resolved |
| Report preview & PDF download | Complete | Formatted PDF with per-student breakdown |
| Semester & yearly reports | Complete | 2 per year + yearly spanning 4–5 years |
| Multi-departmental courses & programmes | Complete | ProgrammeDepartment junction table; courses span depts |
| Lecturer course scope restriction | Complete | Lecturer sees only their assigned courses' records |
| Forgot password fix | Complete | Password update correctly persists to database |
| Admin code gate (routing fixed) | Complete | Super-admin code required; routing issue resolved |
| Railway + Vercel deployment | Complete | Publicly accessible; CORS and env vars configured for production |

## 3.3 Out-of-Scope Boundaries — Held

| Out-of-Scope Item | Introduced? | Notes |
| --- | --- | --- |
| Mobile application (iOS/Android) | No | Web-only; responsive design but not a native app |
| Integration with existing NUL systems | No | Standalone system; no connection to NUL infrastructure |
| Financial / fee management | No | Not requested; not built |

# 4. Schedule Review

| Phase | Planned Dates | Actual Dates | Variance | Assessment |
| --- | --- | --- | --- | --- |
| Initiation & Planning | W1–W2 (16–27 Feb) | W1–W2 | On time | Met |
| Risk Plan | W2–W3 (23 Feb – 6 Mar) | W2–W3 | On time | Met |
| Analysis & System Models | W3–W5 (2–20 Mar) | W3–W5 | On time | Met |
| Design & UI Prototype | W4–W6 (9–27 Mar) | W4–W7 (accelerated — externally imposed deadline) | Compressed by external deadline | Accelerated — external deadline |
| Implementation (CR-002 ext.) | W5–W8 → extended to W8+ | W5 – 10 Apr | Extended per CR-002 | Managed |
| Testing & UAT | W8–W10 (6–24 Apr) | W9–W10 (shortened due to external deadline) | Compressed — external deadline | Completed under externally imposed pressure |
| Closure & Handover | W11–W12 (27 Apr – 10 Apr) | W11–W12 | On time | Met |

# 5. Quality Review

| Quality Area | Standard Set | Outcome | Rating |
| --- | --- | --- | --- |
| Code review compliance | 100% PRs reviewed before merge | 100% maintained throughout — no exceptions | Excellent |
| TypeScript compile errors at submission | 0 errors | 0 errors at final submission | Excellent |
| Functional requirements (FR-01 to FR-31) | All Must Have delivered | All 25 Must Have FRs delivered; 6 Should Have FRs delivered | Excellent |
| Non-functional requirements (NFR-01 to NFR-10) | All Mandatory NFRs met | NFR-01 through NFR-10 all met or substantially met | Excellent |
| Database schema integrity | All 9 Prisma models migrated cleanly | 9 models live in production MySQL on Railway | Excellent |
| Test coverage | All CRUD flows and role flows tested | All major flows tested in initial testing; forgot password and auth edge cases caught and fixed | Good |
| Deployment stability | System publicly accessible and stable | headcount-nine.vercel.app stable; Railway backend uptime maintained | Good |
| Documentation completeness | All 21 deliverables produced | All 21 deliverables complete; 2 change requests formally processed | Excellent |
| Schedule adherence | All milestones on time | The deadline was moved forward by the course lecturer, outside the team’s control. The team successfully met it, but the compressed timeline meant that testing, polish, and documentation were completed under significant external pressure rather than at the pace the team would have chosen. | Met — despite external deadline change |

# 6. Team Performance Review

| Member | Student No. | Key Contribution | Rating |
| --- | --- | --- | --- |
| Makhang, L.M. | 202322596 | Project lead; Initiation & Closure documentation; scope and change management; stakeholder analysis | Good |
| Tsita, S.T. | 202322646 | Analysis phase; system models; business rules; Planning documentation; risk management | Good |
| Manyeli, H.M. | 202002241 | UI prototype (Figma); React/TSX frontend; role theming; CSS dark mode refactor | Good |
| Rakoloi, B.R. | 202321274 | Node.js backend; Prisma schema; MySQL; Railway deployment; attendance session logic | Good |

# 7. Change Request Retrospective

| CR | Raised | Reason | Impact | Handled Well? |
| --- | --- | --- | --- | --- |
| CR-001 | 16 Mar 2026 | TKinter is a desktop framework; project is web-based; Figma maps to React naturally | Low — stack change absorbed within W5; no scope or deadline change | Yes — formal CR raised promptly; team regrouped without disruption |
| CR-002 | 1 Apr 2026 | 15 features identified from active development, testing, and review of the running system | Moderate — features were formalised and delivered within the externally shortened timeline. The team did not set this deadline; it was imposed by the course lecturer mid-sprint | Yes — all features implemented and delivered. The defining characteristic of the Execution phase was the externally imposed deadline compression, documented in the QA Report and Team Performance Report |

# 8. Risk Retrospective

| Risk (from Risk Plan) | Did It Occur? | Actual Impact | Management Outcome |
| --- | --- | --- | --- |
| Team member unavailability | Rarely — competing academic workloads | Low — redistributed via ClickUp task board | Effective |
| Scope creep | Yes — CR-002 added 15 features | Moderate — managed via formal CR; extension granted | Effective |
| Technology issues | Yes — TKinter incompatibility (CR-001); deployment CORS/env var issues | Medium — resolved; no permanent schedule impact | Effective |
| Schedule overrun | Yes — Deadline was moved forward by the course lecturer, outside the team’s control, compressing the entire execution phase | High in effort — the team absorbed an externally imposed deadline change mid-phase and delivered all features, deployment, and documentation on time regardless | Managed |

# 9. Overall Verdict

HEADCOUNT is assessed as a successfully completed project. A fully functional, publicly deployed attendance management system is live at headcount-nine.vercel.app. All primary objectives were met, all in-scope and CR-002 features were delivered, and the system is accessible to real users with role-based access, a working attendance code flow, an audit log, and downloadable reports.

The project produced 21 project management and SDLC documents, 2 formal change requests, 31 functional requirements (FR-01 to FR-31), 10 non-functional requirements (NFR-01 to NFR-10), and a complete 9-model Prisma schema deployed to production MySQL. The team's handling of a technology pivot, a major mid-project scope expansion, and production deployment in a 12-week academic timeline represents a strong outcome by any measure.

# 10. Sign-Off

| Role | Name / Student No. | Date |
| --- | --- | --- |
| Project Lead | Makhang, L.M. — 202322596 | 10 April 2026 |
| Team Member | Tsita, S.T. — 202322646 | 10 April 2026 |
| Team Member | Manyeli, H.M. — 202002241 | 10 April 2026 |
| Team Member | Rakoloi, B.R. — 202321274 | 10 April 2026 |

Prepared by the CS3430 Project Team — National University of Lesotho