National University of Lesotho

Department of Mathematics and Computer Science

HEADCOUNT — NUL Attendance Management System

CS3430: System Analysis and Logical Design

Project Closure Report

HEADCOUNT — Formal Project Completion & Handover

System Name: HEADCOUNT (NUL Attendance Management System)

Production URL: headcount-nine.vercel.app

Tech Stack: React/TypeScript (Vercel) · Node.js/Express + Prisma (Railway) · MySQL

Project Period: 16 February 2026 – 10 April 2026

Closure Date: 10 April 2026

Prepared by: All Team Members — CS3430

# 1. Project Overview

HEADCOUNT is a web-based student attendance management system developed for the National University of Lesotho. The system replaces manual, paper-based attendance registers with a fully digital solution accessible at headcount-nine.vercel.app. The frontend is built with React and TypeScript and deployed on Vercel; the backend is a Node.js/Express REST API using Prisma ORM connected to a MySQL database hosted on Railway.

The project was undertaken over 12 weeks as the primary deliverable for CS3430: System Analysis and Logical Design, by a four-member student team. It encompasses a complete software development lifecycle from project charter through to formal closure, documented across various project management and SDLC artefacts. The project was delivered under significant external time pressure: the project deadline was moved forward to 10 April 2026 by the course lecturer, earlier than the team’s original implementation plan. This externally imposed change, outside the team’s control, compressed the available development window and required the team to accelerate delivery of all remaining features, integration, deployment, and documentation simultaneously.

# 2. System Delivered

## 2.1 Architecture

| Layer | Technology | Deployment |
| --- | --- | --- |
| Frontend | React + TypeScript (TSX), CSS per-role theming | Vercel — headcount-nine.vercel.app |
| Backend | Node.js + Express REST API, Prisma ORM | Railway |
| Database | MySQL (managed via Railway) | Railway |
| Auth | JWT (token), bcrypt password hashing | Backend |
| ORM / Schema | Prisma — 9 models defined and migrated | Railway/MySQL |

## 2.2 Database Schema Delivered

| Model | Key Fields |
| --- | --- |
| User | id, name, email, password, role, studentId, staffId, departmentId, programmeId, yearOfStudy, phone, createdAt, updatedAt |
| Course | id, name, code, description, year, credits, maxEnrollment, departmentId |
| Department | id, name |
| Programme | id, name → ProgrammeDepartment (many-to-many) |
| StudentCourse | studentId, courseId, enrolledAt |
| LecturerCourse | lecturerId, courseId, assignedAt |
| AttendanceRecord | id, courseId, studentId, markedById, date, status (present/late/absent) |
| AttendanceSession | id, courseId, code, phase, classDuration, expiresAt |
| ActivityLog | id, category, action, detail, severity, performedBy, performedByName, timestamp |
| roleenum | value |

## 2.3 Features Delivered

| Feature | Description | Status |
| --- | --- | --- |
| Role-based access control | Admin, Lecturer, Student — JWT-enforced via Express middleware | Complete |
| Two-factor admin login | Secret code gate required before admin session is established | Complete |
| Attendance code system | Lecturer generates random code; 15-min timer; present/late distinction | Complete |
| Session duration choice | Lecturer selects 50-min or 1hr 50-min class duration | Complete |
| Session persistence | Session survives lecturer page navigation; explicit end required | Complete |
| Manual attendance override | Lecturer can manually mark students who cannot submit code | Complete |
| Programme-based enrolment | Multi-departmental programmes via ProgrammeDepartment junction | Complete |
| Per-role colour theming | Admin: red/orange · Lecturer: forest/ocean · Student: default/royal | Complete |
| Dark/light mode | System-wide via CSS prefers-color-scheme; white patches resolved | Substantially complete |
| Activity audit log | All admin actions logged with category, action, detail, severity | Complete |
| Attendance percentage tracking | Late = 50% weighting; low-attendance flag surfaced in UI | Complete |
| Report preview & download | Formatted PDF reports previewable and downloadable from UI | Complete |
| Semester & yearly reports | 2 per academic year + yearly spanning 4–5 years of study | Complete |
| Forgot password | Password reset flow correctly updates database record | Complete |
| Deployment | Frontend on Vercel, backend + DB on Railway, production CORS configured | Complete |

# 3. Scope Completion

| In-Scope Item | Delivered | Notes |
| --- | --- | --- |
| User authentication (JWT login/logout) | Yes | All three roles; admin requires secret code |
| Role-based access control | Yes | Admin, Lecturer, Student — enforced at API level |
| Student registration & profile management | Yes | Admin CRUD with programme-department linkage |
| Course creation & management | Yes | Multi-departmental; courses listed per dept per year |
| Lecturer assignment to courses | Yes | Admin assigns; reflected immediately in My Classes |
| Attendance CRUD by lecturers | Yes | Code-based + manual override; present/late/absent |
| Automated attendance report generation | Yes | Preview + PDF/CSV download; semester and yearly scope |
| Attendance percentage & low-attendance alerts | Yes | Late = 50%; flag surfaced in student and lecturer UI |
| Activity audit log | Yes | Full log for all admin actions |
| Mobile application | No (Out of Scope) | Excluded — web-only per Project Scope Document |
| Integration with existing NUL systems | No (Out of Scope) | Excluded per Project Scope Document |
| Production cloud hosting | Yes (Academic) | Vercel + Railway — publicly accessible |

# 4. Change Requests Processed

| CR | Title | Date | Outcome |
| --- | --- | --- | --- |
| CR-001 | Frontend Technology Stack — Python/TKinter to TypeScript/React | 16 March 2026 | Approved & Implemented — no scope or deadline impact |
| CR-002 | Feature Scope Additions — Attendance Code, Theming, Reporting, Deployment | 1 April 2026 | Approved & Implemented — deadline extended to 10 April 2026 |

# 5. Triple Constraint Final Assessment

| Constraint | Baseline | Final Outcome | Status |
| --- | --- | --- | --- |
| Scope | All in-scope features as defined in Project Scope Document | All in-scope features delivered plus CR-002 additions | Met + Extended |
| Time | 16 Feb – 10 April 2026 (12 weeks) | 16 Feb – 10 April 2026. The deadline was brought forward by the course lecturer, not the team. This external change compressed the implementation window and required the team to deliver all remaining features, deployment, and documentation under a shortened, externally imposed timeline. | Met |
| Cost | Zero licensing cost; optional hosting M0–M300 | Zero licensing cost; Railway + Vercel free tier used | Met |

# 6. Formal Project Closure

The HEADCOUNT — NUL Attendance Management System project is hereby formally closed. The system is live at headcount-nine.vercel.app. Despite the project deadline being moved forward by the course lecturer — outside the team’s control — the team successfully delivered all features, a live deployed system, and all documents by 10 April 2026. All project deliverables have been completed and submitted. All project activities are concluded and the team is released from project responsibilities.

| Role | Name / Student No. | Date |
| --- | --- | --- |
| Project Lead | Makhang, L.M. — 202322596 | 10 April 2026 |
| Team Member | Tsita, S.T. — 202322646 | 10 April 2026 |
| Team Member | Manyeli, H.M. — 202002241 | 10 April 2026 |
| Team Member | Rakoloi, B.R. — 202321274 | 10 April 2026 |

Prepared by the CS3430 Project Team — National University of Lesotho