National University of Lesotho

Department of Mathematics and Computer Science

Project Management Plan

NUL Attendance Management System

CS3430: System Analysis and Logical Design

16th February 2026 – 8th May 2026

Prepared by:

202002241 – Manyeli, H.M.

202321274 – Rakoloi, B.R.

202322646 – Tsita, S.T.

202322596 – Makhang, L.M.

# 1. Introduction

This Project Management Plan (PMP) governs the planning, execution, and closure of the NUL Attendance Management System project. It defines the methodology, roles, communication protocols, risk management strategies, and quality standards the project team will follow throughout the project lifecycle.

## 1.1 Project Overview

NUL currently relies on manual attendance registers which are time-consuming, error-prone, and difficult to analyse. This project will deliver a web-based Attendance Management System that digitises attendance recording, storage, and reporting, improving record accuracy by at least 90%.

## 1.2 Project Objectives

- Develop a secure login system for administrators and lecturers.

- Implement CRUD operations for attendance records.

- Generate automated attendance summary reports.

- Deliver a tested, deployable system by 8 May 2026.

# 2. Project Organisation

## 2.1 Team Roles

| Student No. | Name | SDLC Role | PM Role |
| --- | --- | --- | --- |
| 202322596 | Makhang, L.M. | Planning | Initiation |
| 202322646 | Tsita, S.T. | Analysis | Planning |
| 202002241 | Manyeli, H.M. | Design | Execution |
| 202321274 | Rakoloi, B.R. | Implementation | Execution |

# 3. Schedule Management

## 3.1 Project Timeline

| Weeks | Activity | Dates | Owner SN |
| --- | --- | --- | --- |
| W1–W2 | PM Initiation & Planning | 16 Feb – 27 Feb 2026 | 202322596 |
| W2–W3 | Risk Plan | 23 Feb – 6 Mar 2026 | 202322646 |
| W3–W5 | Analysis & System Models | 2 Mar – 20 Mar 2026 | 202322646 |
| W4–W6 | Design & UI Prototype | 9 Mar – 27 Mar 2026 | 202002241 |
| W5–W8 | Implementation | 16 Mar – 10 Apr 2026 | 202321274 |
| W8–W10 | Testing & UAT | 6 Apr – 24 Apr 2026 | All Members |
| W11–W12 | Closure & Handover | 27 Apr – 8 May 2026 | All Members |

# 4. Communication Management

## 4.1 Communication Plan

| Type | Frequency | Audience | Tool |
| --- | --- | --- | --- |
| Team Stand-up | Weekly | Project Team | In-person |
| Progress Report | Weekly | Project Team | Google Docs |
| Document Sharing | Ongoing | All Stakeholders | Google Drive |
| Issue Tracking | As needed | Project Team | ClickUp |

# 5. Risk Management

## 5.1 Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Team member unavailability | Medium | High | Cross-train members; redistribute tasks early |
| Scope creep | Medium | High | Follow Project Scope; log all change requests |
| Technology issues (MySQL, VS Code) | Low | Medium | Use open-source alternatives; maintain offline backups |
| Hosting cost overrun | Low | Low | Use free-tier hosting during development |

# 6. Quality Management

Quality will be maintained through peer code reviews, unit testing, and user acceptance testing (UAT). Attendance record accuracy must reach at least 90% as defined in the project charter. All deliverables will be reviewed against the WBS checklist before submission.

# 7. Change Management

All change requests must be submitted in writing to the project team. Changes will be assessed for impact on scope, time, and cost. Only approved changes will be incorporated, and the change log will be maintained in Google Drive.

# 8. Closure Criteria

- All WBS deliverables completed and signed off.

- UAT passed with at least 90% accuracy threshold.

- Closure report and lessons-learned document submitted.

- Final system deployed and handover to NUL ICT Department completed.